## ADLAF
Time Log for: | Lee Adlaf |  | Blazer ID: | ADLAF
Log is for all work relarted to P4 starting after the submission of P3
[6 empty] | Lines of code | Hours
Date: | Start time: | Stop time: | Interruptions: | Time taken: | Comments: | written: (est) | worked:
2013-11-10 | 19:30 | 21:00 | 0 | 0 | Android ADT research | 0 | 1.5
2013-11-12 | 17:00 | 18:15 | 0 | 0 | Team Meeting | 0 | 1.25
2013-11-14 | 12:30 | 14:00 | 0 | 0 | Started reporistory on GitHub, Added Folders | 0 | 1.5
2013-11-15 | 15:30 | 17:15 | 0 | 0 | Created test program icon, android ADT research | 0 | 1.75
2013-11-20 | 10:30 | 13:00 | 1 | 0:30 | Function 'Hello World', collection app framework | 10 | 2
2013-11-21 | 9:00 | 12:00 | 1 | 1:00 | GUI work, screen layouts, buttons, tests | 15 | 2
2013-12-01 | 16:30 | 21:00 | 1 | 1:30 | GUI work, themes, using phone as test device | 10 | 3
2013-12-02 | 21:30 | 23:45 | 0 | 0 | GUI work, screen linking via button clicks | 20 | 2.25
2013-12-03 | 9:00 | 12:15 | 0 | 0 | GUI work, screen linking, multi buttons | 20 | 3.25
2013-12-04 | 21:30 | 0:30 | 1 | 0:30 | Dynamic list view testing | 25 | 2.5
2013-12-03 | 17:00 | 18:15 | 0 | 0 | Team Meeting | 0 | 1.25
2013-12-05 | 9:00 | 14:15 | 1 | 1:00 | Dynamic list view testing, refactoring | 20 | 4.25
2013-12-05 | 17:00 | 18:15 | 0 | 0 | Team Meeting | 0 | 1.25
2013-12-06 | 9:00 | 12:00 | 1 | 0:30 | Button fixes, added more screens | 10 | 1.5
2013-12-06 | 12:00 | 13:00 | 0 | 0 | Partial Team meeting | 0 | 1
2013-12-08 | 20:00 | 20:30 | 0 | 0 | Minor comment updates, package name fix | 4 | 0.5
2013-12-09 | 9:00 | 10:00 | 0 | 0 | GUI work - passing information | 10 | 1
2013-12-10 | 11:00 | 15:00 | 1 | 0:30 | GUI work - passing information, new screens | 15 | 3.5
2013-12-11 | 13:00 | 15:00 | 0 | 0 | Team Meeting - Technical Debt / Final assignments | 0 | 2
2013-12-11 | 15:30 | 1:30 | 3 | 3:30 | GUI work - cleanup, test arraylists for presentation | 50 | 6.5
2013-12-12 | 9:00 | 13:00 | 1 | 0:30 | Project paperwork - time log, retrospective, etc | 0 | 2.5
2013-12-12 | 15:15 | 16:15 | 0 | 0 | Final Team meeting - presentation prep | 0 | 1
[6 empty] | Total Hours: | 47.25
[6 empty] | Total Lines of Code: | 209
[6 empty] | Average Code Lines Per Hour: | 4.4233